## Sheet1
引用编号 | 版本 | 冲刺号 | 分类 | 标题 | 故事 | 类型 | 进度 | 初始估计（h） | 优先级 | 如何演示 | 商业价值 | 理想时间（h） | 调整因子 | 复杂度 | 信息度 | 备注
1 | 1 | 1 | user story | 注册配置 | 作为系统管理员，我希望能管理注册类型、注册开关、邮箱验证类型、手机验证类型，以便于扩充注册方式，提供更加方便快捷的注册方式。 | Initial Feature | Not Done | 2 | 98 |  |  | 2
2 | 1 | 1 | user story | 登录配置 | 作为系统管理员，我希望能管理快捷登录开关、登录提示开关，第三方邮箱管理，以便于提供更加快捷的登录方式。 | Initial Feature | Not Done | 1 | 98 |  |  | 2 | 0
3 | 1 | 1 | user story | 用户信息管理 | 作为系统管理员，我希望对所有账号进行查看和管理，以便于系统管理所有账号和密码，保证安全性。 | Initial Feature | Not Done | 2 | 95 |  |  | 2
4 | 1 | 1 | user story | 权限组管理 | 作为系统管理员，我希望能根据网站需求设置对应的权限组，以便于赋予不同权限组不同权限，对前台和后台进行管理。 | Initial Feature | Not Done | 1 | 90 |  |  | 1 | 0
5 | 1 | 1 | user story | 模块权限管理 | 作为系统管理员，我希望能管理在不登录状态下哪些模块不能被访问，以便于增加系统安全性。 | Initial Feature | Not Done | 1 | 85 |  |  | 1 | 0
7
1 | 2 | 2 | user story | 数据统计 | 作为系统管理员，我希望能查看网站的详细统计，如网站统计、用户在线列表，以便于详细了解网站的使用情况 | Initial Feature | Not Done | 2 | 55 |  |  | 2 | 0
2 | 2 | 2 | user story | 敏感词 | 作为系统管理员，我希望能管理设置系统敏感词，以便于过滤敏感词汇，营造良好文明的网路环境。 | Initial Feature | Not Done | 2 | 55 |  |  | 2 | 0
3 | 2 | 2 | user story | 公告 | 作为系统管理员，我希望能在后台发布前台公告，以便于便捷地公布一些需要所有用户都需要了解的消息。 | Initial Feature | Not Done | 3 | 52 |  |  | 2 | 0
4 | 2 | 2 | user story | 友情链接 | 作为系统管理员，我希望能在前台设置友情链接引导用户更加快捷进入推荐网站，以便于增加网站的丰富性和便捷性。 | Initial Feature | Not Done | 1 | 43 |  |  | 1
5+A12:Q12 | 2 | 2 | user story | 广告配置 | 作为系统管理员，我希望能在不同模块管理广告位，以便于对系统的广告设置进行系统有效地管理。 | Initial Feature | Not Done | 1 | 40 |  |  | 1
Note on A1: Luc Segers: This reference ID should be unique. This number is used throughout the whole worksheet so be aware.
Note on B1: Luc Segers: This is the release where the story will be developped
Note on C1: Luc Segers: This is the sprint where the story will be developped
Note on D1: Luc Segers: This is a category to which the story belongs. Example : Infrastrucuture, Back-End, Animation, ...
Note on F1: Luc Segers: This is the story (Feature, Epic, User). Depending on in which phase you are in (Présales, Scope, …) the detail could be higher. Normally you could describe a user story as follow: As a <Role> I can do <this> and the result is <that> ... Offcourse this is not always possible, so you should be creative. A story should conduct to the following rules: I = Independent N = Negotiable V = Valuable to customer E = Estimatable S = Small T = Testable
Note on G1: Luc Segers: Type of the story.
Note on H1: Luc Segers: Status of the story
Note on I1: Luc Segers: This column is calculated: Ideal Hours * Adjustment Factor
Note on J1: Luc Segers: M = Must Have S = Should Have C = Could Have W = Won't have this time
Note on L1: Luc Segers: 0 = Lowest Business Value 100 = Highest Business Value
Note on M1: Luc Segers: Enter here the new ideal estimates which are done with planningpoker
Note on N1: Luc Segers: This column is calculated based on the values of complexity and information. The data is looked up in the setup tab.
Note on O1: Luc Segers: Complexity 0 = Not Defined 1 = Very Simple 2 = Simple 3 = Moderate 4 = Complex 5 = Extreme Complex
Note on P1: Luc Segers: Information 0 = Not Defined 1 = No information 2 = Little information 3 = Moderate information 4 = Much information 5 = All information